## Sheet1
Issue | Assigne | Andrew | Adam | Anthony | Estimated Story Points | Notes
Phase One
Purchase Office | Andrew | 1 | 13 | 1 | 5 | Rent an office space to be used as the Disaster Division HQ.
Office Setup | Anthony | 5 | 8 | 3 | 5 | Set up the office with equipment.
Purchase Transportation | Andrew | 8 | 2 | 13 | 8 | Purchase vehicles to be used in the distrobution of aid and SAR.
Purchase Team Resources | Anthony | 13 | 2 | 8 | 8 | Purchase equip to be used in SAR operations.
Scout Potential Recruits | Adam | 21 | 21 | 21 | 21 | Scout potential recruits/volunteers for SAR teans.
Declare Disasters | Anthony | 8 | 3 | 5 | 8 | Declare the natural disasters that occur in Iron Spell Shores.
Identify Local Emergency Personnel | Adam | 5 | 8 | 8 | 8 | Identify The Local Emergency Personnel In The IronSpell Shore Area: Fire, Police, National Guard, Reserves, Armed Forces.
Assemble Disaster Division Team | Adam | 5 | 5 | 8 | 5 | Assemble the Disaster Division: Create roster, allocate the team resources, HQ rundown, team objectives meeting.
Purchase Kit Resources | Andrew | 13 | 8 | 5 | 8 | Purchase supplies necessary to create emergency aid kits.
Assemble Emergency Kits | Anthony | 5 | 8 | 5 | 8 | Assemble the emergency aid kits.
Package Emergency Kits | Anthony | 3 | 13 | 5 | 5 | Package the emergency aid kits for distrobution.
Zone Breakdown | Andrew | 5 | 5 | 5 | 5 | Divide Ironspell Shore into sectors for teams to be deployed to.
Safe Haven Declaration | Andrew | 3 | 3 | 5 | 3 | Declare locations as safe havens for shelter and aid.
Create Ideal Action Plan | Andrew | 21 | 13 | 8 | 21 | Define what teams will cover which zones during a disaster.
Pack Trucks with Emergency Kits | Anthony | 3 | 3 | 3 | 3 | Pack trucks with emergency kits for rapid deployment to safe havens.
Local Personnel Deployment Plan | Anthony | 5 | 5 | 5 | 5 | Create plan for the deployment of local emergency services to areas in need.
Clean Up Plan | Andrew | 13 | 21 | 5 | 13 | Create clean up plan to define which zones are essential for infrastructure.
| Storypoint Total | 137 | 141 | 113 | 139
Phase Two
Define Zone Deployment Plan | Andrew | 3 | 3 | 3 | 3 | Assign teams to zones.
Define Emergency Personnel Aid Plan | Andrew | 5 | 3 | 3 | 3 | Coordinate with local emergency services for assitance.
Define Transportation Plan | Andrew | 3 | 3 | 3 | 3 | Create transportation plan for those in immediate need.
Deploy Division Aid to The Public | Adam | 21 | 21 | 13 | 21 | Deploy teams to the public.
Identify Local Personnel to Assit Division | Adam | 5 | 5 | 5 | 5 | Identiffy who will help the Disaster Division.
Deploy Local Personnel to Aid | Adam | 3 | 3 | 1 | 3 | Deploy local personnel to assist the Disaster Division.
Pack Trucks | Anthony | 1 | 1 | 2 | 2 | Ensure trucks are packed with supplies.
Fuel Trucks | Anthony | 1 | 1 | 1 | 1 | Fuel the trucks for transportation.
Truck Send Off | Anthony | 1 | 1 | 1 | 1 | Send trucks to safe havens to deliver aid kits.
Public Resource Monitoring | Anthony | 5 | 3 | 3 | 3 | Monitor the public to determine who needs resources, and distribute aid kits accordingly.
Disaster Monitoring | Anthony | 5 | 3 | 3 | 3 | Monitor the disaster to where it is headed and when it will end.
Broadcasts | Anthony | 5 | 1 | 3 | 3 | Hold broadcasts during the disaster to help people find safety and deliver crucial information.
End of Disaster | Anthony | 1 | 1 | 1 | 1 | Declare the end of the natural disaster.
| Storypoint Total | 59 | 49 | 42 | 52
Phase Three
Medical Response | Andrew | 8 | 5 | 1 | 5 | Determine who needs immediate medical attention / transport.
Fire Response | Andrew | 5 | 5 | 1 | 5 | Respond to fires that are threating and causing damage.
Evacuations | Andrew | 8 | 13 | 1 | 8 | Evacuate all those in need.
Account For Civilians | Anthony | 13 | 21 | 13 | 21 | Take count of all civilians.
Declare Casualties | Anthony | 5 | 3 | 2 | 5 | Declare casualties.
Population Count | Anthony | 8 | 3 | 5 | 5 | Conduct a count of the population.
Missing Persons in Search | Anthony | 13 | 13 | 13 | 13 | Start a missing persons search.
Aid in Clean Up | Adam | 8 | 13 | 8 | 13 | Start aiding in the clean up of the debris left from the disaster.
Repair Hospitals | Adam | 13 | 21 | 13 | 21 | Repair hosptials.
Repair Schools | Adam | 8 | 13 | 13 | 13 | Repair schools.
Repair Legal Offices | Adam | 8 | 13 | 13 | 13 | Repair legal offices.
Repair Markets | Adam | 8 | 8 | 13 | 8 | Repair food outlets.
Start Monthly Check-Ins | Adam | 5 | 2 | 2 | 3 | Start monthly check ins to ensure the community is recovering at a good rate.
| Storypoint Total | 110 | 133 | 98 | 133